## Sheet1
person	date	what	hours	eric	john	seb	pierre h	pierre m	ludi
eric	15-01-12	Converting the git repos		4
john, eric	25-01-12	Architecture meeting		1	1
eric	27-01-12	Making an indexhibit clone		3
eric	30-01-12	Temporary front-page restyle		4
eric	02-02-12	Start of the git viewer		1
eric	07-02-12	osp web fonts		1
seb, eric	08-02-12	design meeting		2		2
eric	09-02-12	git viewer: templating		3
john	09-02-12	Visual git viewer			3
eric	10-02-12	git viewer: ui		1
john	10-02-12	Visual git viewer			10,5
john	13-02-12	Visual git viewer			5,5
john	14-02-12	Visual git viewer			3,5
eric	14-02-12	git viewer: installation instructions ubuntu		3
eric	14-02-12	git viewer: troubleshooting		1
john	15-02-12	Visual git viewer			8
john	16-02-12	Visual git viewer			5
eric	16-02-12	git viewer: transducer on front end		3
eric	17-02-12	git viewer: ui with breadcrumbs and icons		4
eric	24-02-12	redo gallery theme as bootstrap		2
john	25-02-12	Visual git viewer			4
eric	25-02-12	git viewer: the night we refactored and implemented the cache		4
eric	26-02-12	git viewer: multi-repository support		2
john	28-02-12	Visual git viewer			4
john	01-03-12	Visual git viewer			3
eric	04-03-12	converted last indexhibit to iceberg		3
eric	05-03-12	osp bootstrap		1
pierre, pierre, eric	30-03-12	architecture, visual design		3			3	3
ludi, eric	06-05-12	mockup interface		2					3
eric	08-05-12	rad url routing		1

			98,5	49	47,5	2	3	3	3
				885,48	858,38	36,14	54,21	54,21	54,21
		if we want to go for €30/hour we still have	-39,17	hours
		we are actually at a rate of	18,07